## Weekly Gantt Chart Template
Project Topic: Sign Language Interpreter Android Application: LSTM Neural Network
Project Member: Victor Kibiwot
Project Mentor: Chirawat Wattanapanich
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Task name | Progress | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16
ACTION DETECTION MODEL
1 | Proposal | 100%
2 | Proposal Presentation | 100%
3 | LSTM neural net research | 100%
4 | Gathering Requirements | 100%
5 | ASL Sample Selection | 100%
6 | Dataset Preparation | 100%
7 | Train LSTM Model | 100%
8 | Evaluating model | 100%
9 | Fine-tuning sign detection model | 100%
10 | Converting model to tflite | 100%
ANDROID
11 | Graphical User Interface development | 100%
12 | Integrating MP Android Solution API | 100%
13 | Binding tflite model to app | 100%
14 | Performing Inference | 100%
15 | Preparing output as text | 100%
16 | System debugging | 100%
17 | Finalizing Research Paper | 100%
18 | FINAL PRESENTATION | 0%
|  |  | Completed task |  |  |  | Incomplete task |  |  |  | Current task

## Useful Tips
USEFUL TIPS
1 | When enteringactivity start and end dates in columns "D" and "E" use the following date format: DD/MM/YYYY
2 | To change colour of fill and text in cells, use HOME -> FONT tool palette.
3 | To change LOGO image, right click on it and choose CHANGE PICTURE.

## ©
© TemplateLab.com